## User Stories
User Stories | User Stories Description
US-01 | As a user I should be able to register with the application so that I can login and use the functionalities of the application.
US-02 | As a user, I should be able to login with my user name and password in order to access the functionalities of the application.
US-03 | As a user, I should be able to login with my Gmail account in order to access the functionalities of the application.
US-04 | As a user, I should be able to login with my Gmail account in order to access the functionalities of the application.(Optional requirement)
US-05 | As a user, I should be able to save resources to a wishlist/favourite so that I can access them later
US-06 | As a user, I should be able to access items saved to my wishlist/favourite Notes

## Stand up Meet
Day | Impediments | Action Taken
1 | Requirement Analysis | Read the artifact provided by stackroute
2 | Planning | Discussed with team members
3 | Designing the wireframe | Discussed with team members
4 | Division of task of frontend | Discussed with team members
5 | Error in footer module | Discussed with team members
6 | Error in user service module | Try to resolve but didn't get resolved
7 | Task Division of backend | Discussed with team members
8 | Error in update profile module | Prudviteja came with a idea and later worked upon that
9 | Error in cors configuration | Discussed with team members
10

## Task Devision
Task | Task Description | Assigned to | State
1 | Creating header component | Sandeep Modugu | Completed
2 | Creating footer component | Sandeep Modugu | Completed
3 | Creating Favourite component | Lambu Narendra | Completed
4 | Creating Update Profile component | Lambu Narendra | Completed
5 | Creating Login component | Prudviteja Bandam | Completed
6 | Creating Registeration Component | Prudviteja Bandam | Completed
7 | Creating Main Component | Shivam Tiwari | Completed
8 | Creating Service for Components | Shivam Tiwari | Pending
9 | Creating Gateway in backend | Lambu Narendra | Completed
10 | Creating Eureka Server in Backend | Lambu Narendra | Completed
11 | Creating User microservice in backend | Prudviteja Bandam | Completed
12 | Creating WatchList or fav microservice in backend | Shivam Tiwari | Completed
13 | Creating JWT authentication microservice in backend | Sandeep Modugu | Pending